## Sheet1
CULTURE TIMELINE
DATE | TASK | WHO | DONE
PRE-EVENT
Select Proposed Date
Submit Event Proposal Request
Place Approved Date on Calendar
Set Dates for 120, 90, 60, and 30 Day Meetings
12 WEEKS OUT
Create Registration Form & Submit to Communications
Launch Online Camper Registration
Determine Camp Theme
Create Budget & Budget Spreadsheet
Create 90 Day Meeting Agenda
90 Day Meeting
Create Artwork for Promo Cards
Discuss Promo Card Orders with Campus Pastors
Have Promotion Campaign Meeting
Create 60 Day Meeting Agenda
60 Day Meeting
Order Promo Cards
Submit Church Reservations
8 WEEKS OUT
Create T-Shirt & Merch Artwork (marketing)
Select Core Leaders
Create Online Volunteer Registration Form
Plan Post Service Sessions
Have After Party Planning Meeting
Begin Asking/Selecting Volunteers
Communicate Production Needs with Tech Arts
6 WEEKS OUT
Schedule Core Leader Meeting
Schedule Big Leader Meeting
Brightsigns Request
Review Event Budget with Event Oversight
Create Primary Event Schedule
Establish Preaching Schedule
Meet w/ Worship to Establish Worship Detail
Lock Down Videographer/ Photographer
5 WEEKS OUT
Continue Volunteer Hunt
Lock In Activities Overseer & Shopper
Create Food Truck Menu
Create & Order Culture Wristbands (marketing)
Reserve Inflatables and Order All After Party Supplies
4 WEEKS OUT
Continue Volunteer Hunt
Order T-Shirts
Lock In Worship Leaders
Meet w/ Worship Leader Over Song Choices
Begin Assigning Volunteers to Positions
Create 30 Day Meeting Agenda
30 Day Out Meeting
Review Event Budget with Event Oversight
Determine Leader Meeting Food
Email P. Ken about Golf Carts
3 WEEKS OUT
Create Activities Map
Create Service Map
Continue Volunteer Hunt
Continue Placing Leaders
Send Out Core Leader Metting Invite
Create Core Leader Meeting Agenda
Create Big Leader Meeting Agenda
Send Out Big Leader Meeting Invites
Invite All Students via Text to Culture
Make Sure Everything Is Ordered
2 WEEKS OUT
Send front desk all the Camp Communication
Communicate Content & Maps to Service Team (06/19/24)
Have facilities meeting (06/19/24)
Create Culture Set-Up To-Do List
Create Daily Song Playlist
Go Shopping for concessions
Follow Up With Speakers
Culture is Happening Email
1 WEEK OUT
Send Communication Email to Parents
Finalize Service Detail with Production
Finalize, Print & Handout OOS
Finalize Word Slides
Organize Merch
Finalize Worship Band Needs
Big Leader Meeting (07/08/24)
Speak About Schedule Conflicts with Dream Team
Buy Speaker Thank Yous
Set Up After Parties as Much as Possible