JH Night Timeline

6 Weeks Out:

- Have first meeting with the team to brainstorm potential JH Night locations

- Call potential JH Night locations to get quotes for pricing

- By end of week, have location secured

- Create registration link- update with address, time, cost, and waivers if needed

- Create communication to be sent out to parents when they register their student that includes the address, time, and food we will be providing.

- Determine promotion plan

4 Weeks Out:

- Begin promoting on social media and during post service announcements

- Create communication to be sent out to parents inviting them to register their student- will be sent out week of JH Night

- Begin asking dream teamers to volunteer

- Determine the “spiritual element” of the night (Normally a volunteer sharing a brief testimony)

2 Weeks Out:

- Finalize volunteer list

- Give staff specific roles for the night (who will be handling check in, sign ups at the door, picking up food etc.)

- Determine any last-minute to-dos (purchasing pizza, cookie cake, etc.)

- Continue to promote to students & parents

- Determine any post-event communication